## Product Backlog
Item | Detail | Priority | Status | Estimate time
As a customer, I want to sign in account |  | High |  | 5
As a customer, I want to edit the personal information |  | High |  | 4
As a customer, I want to check my accounts |  | High |  | 2
As a customer, I want to transfer cash of my accounts to others in same bank |  | High |  | 8
As a customer, I want to transfer cash of my accounts to others in other bank |  | High |  | 4
As a customer, I want to deposit online |  | High |  | 4
As a customer, I want to checkout my receipt |  | High |  | 4
As a customer, I want to borrow money online |  | High |  | 4
As a customer, I want to look up to something like where ATMs are |  | Normal |  | 4
As a customer, I want to review my transaction histories |  | High |  | 6

## Sprint Backlog#1
ID | Task | Responsible | Related Task | Status(Not Started In Progress Completed) | Hours of Work Remaining Until Completion (hour)
[5 empty] | T2 | T3 | T4 | T5 | T6 | T7 | CN
1 | Customer Login
| Analysis and Design |  | tinhpt5 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | tinhpt5 | In Progress | 0 | 1 | 0.5 | 0 | 0 | 0 | 0
| Write TestCase |  | tinhpt5 | Done | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
| Acceptance Test |  | tinhpt5 | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  | tinhpt5 | Done | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
2 | FormMenu after customer login
| Analysis and Design |  | phuocbv3 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | phuocbv3 | In Progress | 0 | 0 | 1 | 0 | 0 | 0 | 0
| Write TestCase |  | phuocbv3 | Done | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
| Acceptance Test |  |  | In Progress
| Writing Materials |  |  | In Progress
3 | Edit information of the customer
| Analysis and Design |  | thaonx3 | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0
| Code + Unit Test |  | thaonx3 | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Write TestCase |  | thaonx3 | Done | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| Acceptance Test |  | thaonx3 | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  | thaonx3 | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Retrieve password
| Analysis and Design |  | quannh15 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  |  | In Progress | 0 | 1 | 0 | 0 | 0 | 0 | 0
| Write TestCase |  |  | Done | 0 | 0 | 0 | 0 | 0.25 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | Done | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
5 | Check account imformation
| Analysis and Design |  | quannh15 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  |  | In Progress | 0 | 1 | 0 | 0 | 0 | 0
| Write TestCase |  |  | Done | 0 | 0 | 0 | 0 | 0.25 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | Done | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
6 | Transfer money to other account in same bank
| Analysis and Design |  | quangcm | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | quangcm | In Progress | 0 | 3 | 0 | 0 | 0 | 0 | 0
| Write TestCase |  | quangcm | Done | 0 | 0 | 0 | 0 | 0.25 | 0 | 0
| Acceptance Test |  | quangcm | Done | 0 | 0 | 0 | 0 | 0.25 | 0 | 0
| Writing Materials |  | quangcm | Done | 0 | 0 | 0 | 0 | 0.25 | 0 | 0
7 | Transfer money to other account in other bank
| Analysis and Design |  | quangcm | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | quangcm | In Progress | 0 | 0 | 1 | 0 | 0 | 0 | 0
| Write TestCase |  | quangcm | Done | 0 | 0 | 0 | 0 | 0.25 | 0 | 0
| Acceptance Test |  | quangcm | Done | 0 | 0 | 0 | 0 | 0.25 | 0 | 0
| Writing Materials |  | quangcm | Done | 0 | 0 | 0 | 0 | 0.25 | 0 | 0
8 | Deposit online
| Analysis and Design |  | thaonx3 | Done | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| Code + Unit Test |  |  | In Progress
Write TestCase
| Acceptance Test |  |  | In Progress
| Writing Materials |  |  | In Progress
9 | Liquidate Online
| Analysis and Design |  |  |  | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| Code + Unit Test |  | ducdv13 | In Progress | 0 | 0 | 0 | 1 | 0 | 0 | 0
| Write TestCase |  | ducdv13 | Done | 0 | 0 | 0 | 1 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress
Writing Materials
10 | Borrow money online
| Analysis and Design |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | phuocbv3 | In Progress | 0 | 0 | 0 | 1 | 0 | 0 | 0
| Write TestCase |  | phuocbv3 | done | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
| Acceptance Test |  |  | In Progress
| Writing Materials |  |  | In Progress
11 | Look up something like where ATMs are
| Analysis and Design |  | ducdv13 | done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | ducdv13 | In Progress | 0 | 0 | 0 | 1 | 0 | 0 | 0
Write TestCase
| Acceptance Test |  |  | In Progress
Writing Materials
12 | Review transaction histories
| Analysis and Design |  | tinhpt5 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | tinhpt5 | In Progress | 0 | 0 | 1 | 1 | 0 | 0 | 0
| Write TestCase |  | tinhpt5 | Done | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
| Acceptance Test |  | tinhpt5 | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  | tinhpt5 | Done | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
|  |  |  | Total time | 0 | 6 | 4.5 | 5 | 4.5 | 0 | 0

## Sprint Backlog#2
ID | Task | Responsible | Related Task | Status(Not Started In Progress Completed) | Hours of Work Remaining Until Completion
1 | Customer Login |  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | CN
| Code + Unit Test |  | tinhpt5 | In Progress | 1 | 0.5 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  | tinhpt5 | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | FormMenu after customer login
| Code + Unit Test |  | phuocbv3 | In Progress | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 1 | 0 | 0 | 0 | 0
| Writing Materials |  |  | In Progress | 0 | 0 | 0 | 0 | 1 | 0 | 0
3 | Edit information of the customer
| Code + Unit Test |  | thaonx3 | In Progress | 0 | 0.5 | 0 | 0 | 0.25 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Retrieve password |  | quannh15
| Code + Unit Test |  |  | In Progress | 3 | 0 | 0 | 1 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | In Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0
5 | Check account imformation |  | quannh15
| Code + Unit Test |  |  | In Progress | 1 | 0 | 0 | 0 | 2 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | In Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0
6 | Transfer money to other account in same bank
| Code + Unit Test |  | quangcm | In Progress | 1 | 1 | 1 | 0 | 0 | 0 | 1
| Acceptance Test |  |  | In Progress
7 | Transfer money to other account in other bank
| Code + Unit Test |  | quangcm | In Progress | 1 | 1 | 1 | 1 | 1 | 1 | 0
In Progress
8 | Deposit online
| Code + Unit Test |  |  | In Progress
| Acceptance Test |  |  | In Progress
| Writing Materials |  |  | In Progress
9 | Liquidate Online
| Code + Unit Test |  | ducdv13 | In Progress | 0 | 0 | 0 | 1 | 1
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0
10 | Borrow money online
| Code + Unit Test |  | phuocbv3 | In Progress | 0 | 1 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 1 | 0 | 0
| Writing Materials |  |  | In Progress | 0 | 0 | 0 | 0 | 2
11 | Look up something like where ATMs are
| Code + Unit Test |  | ducdv13 | In Progress | 0 | 0 | 0 | 0 | 1
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0
12 | Review transaction histories
| Code + Unit Test |  | tinhpt5 | In Progress | 0 | 0 | 1 | 1 | 0.5 | 0 | 0
| Acceptance Test |  | tinhpt5 | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total time | 9 | 4 | 5 | 4 | 8.75 | 1 | 1

## Sprint Backlog#3
ID | Task | Responsible | Related Task | Status(Not Started In Progress Completed) | Hours of Work Remaining Until Completion
1 | Customer Login |  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | CN
| Code + Unit Test |  | tinhpt5 | Done | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
| Acceptance Test |  | tinhpt5 | In Progress
2 | FormMenu after customer login
| Code + Unit Test |  | phuocbv3 | Done | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress
| Writing Materials |  |  | In Progress
3 | Edit information of the customer
| Code + Unit Test |  | thaonx3 | Done | 0 | 0 | 0.5 | 0 | 1 | 0
| Acceptance Test |  | thaonx3 | In Progress | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  | thaonx3 | Done | 0 | 0 | 0.5 | 0 | 1 | 0
4 | Retrieve password |  | quannh15
| Code + Unit Test |  |  | Done | 1 | 2 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Check account imformation |  | quannh15
| Code + Unit Test |  |  | Done | 1 | 0 | 2 | 0 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Transfer money to other account in same bank
| Code + Unit Test |  | quangcm | Done | 0 | 0 | 0 | 1 | 0.25 | 0 | 0
7 | Transfer money to other account in other bank
| Code + Unit Test |  | quangcm | Done | 0 | 0 | 0 | 0 | 1 | 0 | 0
8 | Deposit online
| Code + Unit Test |  |  | In Progress
| Acceptance Test |  |  | In Progress
| Writing Materials |  |  | In Progress
9 | Checkout Online
| Code + Unit Test |  | ducdv13 | In Progress | 0 | 0 | 0 | 1 | 1 | 0 | 0
| Acceptance Test |  |  | In Progress
10 | Borrow money online
| Code + Unit Test |  | phuocbv3 | Done | 0 | 1 | 1 | 0 | 1 | 0 | 0
| Acceptance Test |  |  | In Progress
| Writing Materials |  |  | In Progress
11 | Look up to ATMs
| Code + Unit Test |  | ducdv13 | Done | 0 | 0 | 0 | 1 | 1 | 0 | 0
| Acceptance Test |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Review transaction histories
| Code + Unit Test |  | tinhpt5 | Done | 0 | 0 | 1 | 1 | 0 | 0 | 0
| Acceptance Test |  | tinhpt5 | In Progress
|  |  |  | Total | 3 | 4 | 6.5 | 4 | 6.25 | 0 | 0